## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Odd One Out
Group Member: | Allen Muthupunnackal Jose |  | Progress Classes: | Ahead
Group Member: | Lachlan Sexton |  |  | On-track
Group Member: | Anna Mance |  |  | Behind
Group Member: | Nikita Zaytsev |  |  | Way Behind
Tutor: | Nan Gao
Class: | Monday 12:30
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Allen Muthupunnackal Jose | Lachlan Sexton | Anna Mance | Nikita Zaytsev
|  |  | Group Formed |  | Weekly Contribution |  |  |  | Created Repo and MS Group. Added Week 7 LinkedList Implementation
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Allen Muthupunnackal Jose | Lachlan Sexton | Anna Mance | Nikita Zaytsev
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Implemted the addAt method for the LinkedList. And worked on the user prompt for the menu class. | Implemented the deleteBack method for the Linked List. Implemented Menu for Qwirkle. Implemented credits and quit function for Qwirkle. Added colour to Heading of Qwirkle | Created Menu class. Continued work on implentation of Tile, TileBag and Board classes. Updated LinkedList and Node classes to refect new implementation. | Created / worked on Coord, Tile, GameEngine classes. Discussed program structure extensively. Expanded most classes to include components necessary for implemented features.
Initial Design of ADTs (classes and potential methods)
Main menu
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Issues
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
|  |  | ADT implementation for storing information, game loop logic not required |  | Other Notes
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Allen Muthupunnackal Jose | Lachlan Sexton | Anna Mance | Nikita Zaytsev
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Implemented validateName method for the gameEngine class and did some extra implementation on the startNewGame method in gameEngine class. | Implemented the player class, including the tilebag for each player. Started doing testing for the menu and started the implementation of the .save files. | Created Square class, updated Board to implement square objects. Worked on manual testing in main. Created and worked on GameEngine class for game logic. | Implemented save game loading, including some game integration. Implemented tiles being displayed as part of the board.
Initialisation of data strctures for new game
Write Tests Cases for common uses
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
[5 empty] | Issues | Had issues of merge conlicts. |  | Had issues deciding best way to design the classes for completing game logic. | Significant issues with type conversion from/to strings when loading.
Other Notes
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Allen Muthupunnackal Jose | Lachlan Sexton | Anna Mance | Nikita Zaytsev
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Did Error checking of user prmopt, and ran some tests. | Fully implemented the save file, working with the input from the user. including the extractFile. Implemented the randomness to the tilebag aswell as created more tests for the program. Also added the secret menu and the tilebag shuffle, this secret menu allows the same random tilebag to be tested. | Continued work on implemention of GameEngine. Updated other classes accordingly. | Made compilation and merge conflict fixes. Worked on finilasing the logic of the game and making fixes to resolve edgecases. Fixed linkedList deleteAt implementation. Bugtested, resolved some tile placement issues. Implemented EOF user input. Other stuff too.
Full error checking of user prompt
Automated placement of tiles at end of round, but no scoring
|  |  | Final Tests |  | Issues |  | Originally had difficulties producing the seed for the tilebag. | Had difficulty creating functions for validation of user commands. | When merging branches some methods would not overwrite but be redeclared, and it wasn't immediately obvious which was newer. It is challenging attempting to fix an issue in code you haven't written personally, takes quite a while longer.
Group Report Written
Other Notes
|  | Progress | Behind